## START HERE
XRVE / PLANNER JOB READINESS
Evidence-based scheduling gate: readiness is not the same as authorization to perform work.
HOW TO USE
01 | Enter a work order and asset ID, then review all seven readiness gates with the responsible parties.
02 | Use Yes, No or Unknown. Blank is treated as unresolved evidence, never as Yes.
03 | Use the scheduling signal to prepare the frozen schedule and resolve not-ready work ahead of coordination.
04 | Verify permits, isolations, energy control and job risk separately at execution under site procedure.
DECISION BOUNDARIES
01 | Ready for Scheduling Review means all seven planning gates are reported Yes; it does NOT approve LOTO, permits, energization or return to service.
02 | Any No = Not Ready; Unknown/blank = Evidence Incomplete. The decision owner must resolve all exceptions.
03 | Labor and material availability must be physically confirmed against the specific work order and target execution window.
FIELD DEFINITIONS / METHOD
01 | Seven gates: scope, safety prerequisites reviewed, labor, material, tools/access, operations window and dependencies.
02 | Gate coverage counts confirmed Yes values; it is not an overall job quality score.
03 | Required By is a planning need date, not a committed execution promise.
XRVE Reliability ¦ Version 2.0 ¦ 2026-10-10 ¦ White/blue cells accept inputs; shaded result columns contain formulas.

## OVERVIEW
XRVE / SCHEDULING READINESS
MEASURE | VALUE | DECISION INTERPRETATION
Work orders entered |  | Population proposed for planning/review.
Ready for review |  | All planning evidence recorded Yes; still needs execution authorization.
Not ready |  | At least one explicit planning gate marked No.
Evidence incomplete |  | Unknown or missing gate answers.
A scheduling checklist never supersedes LOTO, permit, safety or engineering authorities.

## JOB REGISTER
XRVE / Planner Job Readiness
Yes = evidence verified. No = constraint. Unknown/blank = not yet confirmed.
INPUT: alternating white/blue rows ¦ CALCULATED: darker header ¦ Empty evidence remains unassessed ¦ No output authorizes work or an interval change
WO Number | Asset ID | Scope Defined | Safety Prereqs Reviewed | Labor Estimated | Materials Confirmed | Tools & Access | Operations Window | Dependencies Resolved | Planner / Owner | Needed By | Gate Coverage | Scheduling Signal | Constraint / Next Action